## HRPRD
MINFRA-3365					Comments
HRPRD	HRPRDP01	HRPRDP02	HRPRDP03	HRPRDP04	HRPRDP98	HRPRDP99	HRPRDB01	HRPRDB02
WASPRCS	Done	Done	Done	Done	Done	Done	Done	Done
DB Refresh
Load Balance Integration Broker	TODO	TODO	TODO	TODO	OFF	OFF	OFF	OFF
Process Scheduler	NA	NA	NA	NA	NA	NA	Master	Slave
PRCS: 2-Nodes	TODO
Set up gateway Nodes (PSFT_FS etc.)
Set JVM Heap to 4gigs	2048	2048	2048	2048	4096	4096	2048	2048	ALL Done
Set Appserver JVM to min=32m, Max=256m	NA	NA	NA	NA	NA	NA	NA	NA
Reconfigure appserver to load JVM change: psadmin -c configure -d $ORACLE_SID	NA	NA	NA	NA	NA	NA
Add WS & AS to B01 and B02 (Wayde)	NA	NA	NA	NA	NA	NA	Done	Done
Load Balance B01 and B02 Appservers					Done	Done
Compile COBOL: PS_HOME					LICENSE MANAGER DOWN
Compile COBOL: PS_APP_HOME					LICENSE MANAGER DOWN
Compile COBOL: PS_CUST_HOME					LICENSE MANAGER DOWN
Check Tuxedo Version	tuxedo11gR1.104
Check App Version	HR9.2.05
Check Tools Version	PT8.53.06
Change Report Node to point to B01 (and B02 with second node)	At Go-Live
Verify use of the PROD web profile	Done	Done	Done	Done	Done	Done	Done	Done
Encrypt AS/PRCS MCM Password

## CSPRD
MINFRA-3366					Comments
CSPRD	CSPRDP01	CSPRDP02	CSPRDP03	CSPRDP04	CSPRDP05	CSPRDP06	CSPRDP07	CSPRDP08	CSPRDP98	CSPRDP99	CSPRDB01	CSPRDB02
WASPRCS	Done	Done	Done	Done	Done	Done	Done	Done	Done	Done	NA	NA
DB Refresh
Load Balance Integration Broker	TODO	TODO	TODO	TODO	TODO	TODO	TODO	TODO	OFF	OFF	OFF	OFF
Process Scheduler	NA	NA	NA	NA	NA	NA	NA	NA	NA	NA	Master-Done	Slave-Done
PRCS: 2-Nodes	TODO
Set up gateway Nodes (PSFT_FS etc.)
Set JVM Heap to 4gigs	2048	2048	2048	2048	2048	2048	2048	2048	4096	4096	2048	2048
Set Appserver JVM to min=32m, Max=256m	Done	Done	Done	Done	Done	Done	Done	Done	Done	Done	NA	NA
Reconfigure appserver to load JVM change: psadmin -c configure -d $ORACLE_SID	Done	Done	Done	Done	Done	Done	Done	Done	Done	Done
Add WS & AS to B01 and B02 (Wayde)	NA	NA	NA	NA	NA	NA	NA	NA	NA	NA	Done	Done
Load Balance B01 and B02 Appservers	NA	NA	NA	NA	NA	NA	NA	NA	NA	NA	Done	Done
Compile COBOL: PS_HOME					LICENSE MANAGER DOWN
Compile COBOL: PS_APP_HOME					LICENSE MANAGER DOWN
Compile COBOL: PS_CUST_HOME					LICENSE MANAGER DOWN
Check Tuxedo Version	tuxedo11gR1.104
Check App Version	CS9.0.33
Check Tools Version	PT8.53.06
Change Report Node to point to B01 (and B02 with second node)					TODO on Cutover
Verify use of the PROD web profile	Checked	Checked	Checked	Checked	Checked	Checked	Checked	Checked	Checked	Checked	Checked	Checked
Encrypt AS/PRCS MCM Password					TODO on Cutover

## HRSUP
MINFRA-3368
HRSUP	HRSUPP01
WASPRCS	Done
DB Refresh
Load Balance Integration Broker	NA
Process Scheduler	Done – P01
PRCS: 2-Nodes	NA
Set up gateway Nodes (PSFT_FS etc.)
Set JVM Heap to 4gigs	NA
Set Appserver JVM to min=32m, Max=256m	NA
Reconfigure appserver to load JVM change: psadmin -c configure -d $ORACLE_SID	NA
Add WS & AS to B01 and B02 (Wayde)	NA
Phire Migrations